## main
序 号 | 类型 | 主题 Implementation_TG_v2010EE.dbf | QAD 检索关键字 | 步骤/说明 | 其他 | C-顾问 P-程序 S-销售 | 备注/例子 | 类型 | 1-重要 2-了解 3-可选
0 | 配置 | 导入帮助文件 | 36.4.13.14 | Field Help Load 1) fieldhlp_cbf.fhd 2) fieldhlp.fhd 3) Warehouse.fhd 导入3个CH,3个US | /app/mfgpro/2011.1EE/db/ch/fieldhlp.fhd /app/mfgpro/2011.1EE/db/us/fieldhlp.fhd ** 退出再进去哦！！ | CS |  | 完成 | 2
0.2 | 配置 | 没有安装Crystal Report Runtime | 27.17.9 Customer Aging Analysis by Grp History | The Crystal Reports runtime is not installed yet. The installer will start now. (1) Mount the media and extract [QAD2011.1EE media]\packages\packages\netui-module-fin\2011\0\79\20\netui-module-fin-2011.0.79.20.zip. (2) Extract netui-module-fin-2011.0.79.20\data.zip. (3) Extract data\client\packages\fin-crruntime\fin-crruntime-1.0.0.0.zip. (4) Find directory fin-crruntime-1.0.0.0\plugins\qad.plugin.financials\CRRuntime. The CRRuntime should contain data.zip and manifest.qpkg. (5) Copy the CRRuntime directory and put it under [Tomcat]/webapps/qadhome/packages/plugins/qad.plugin.financials/ | (1) FIND /app/mfgpro/qdt/pstage/netui-module-standard/packages/netui-module-fin/2011/0/79 /20/netui-module-fin-2011.0.79.20.zip (2)Extract File CRRuntime/ * data.zip * manifest.qpkg (3) COPY File To app/tomcat/webapps/qadhome/packages/plugins/qad.plugin.financials/CRRuntime [root@dbserver CRRuntime]# ls data.zip manifest.qpkg |  | Process Map 不见了: XML Dir: WEB-INF/pronav/xml/ch http://192.168.0.55:8080 /app/tomcat/webapps/qadui/WEB-INF/pronav/xml/ch 同一台PC运行2套QAD2011.1EE - 修改ShortCut的目录名 - 修改ShortCut的指向
1 | 概述 | 设置步骤 |  | 0. 务必重新启动Daemon 0.1 XML / 复制 / Balance Deamon 1. System-Wide Setup (系统级别的设定) 2. Domain-Level Setp (Domain级别的设定) 3. Operation Data 设定 4. 模拟测试 （最小功能） Tomcat 启动失败** 注意检查Lock文件 /app/tomcat/logs/pid File | 0. /app/mfgpro/qdt/envs/demo/scripts/startqadfindemo.ksh 0.1 运行 /home/mfg/callmenu 1. For All Domain (可以使用不同Domain进行登陆) 2. 登陆指定的Domain进行设置 3. 旧系统功能设定 4. 进行功能模拟 ** 清单可参考Implementation静/动态设置 A. 提示超过20000Session 时,尝试: ulimit -a (-n 参数) ulimit.conf EDIT B. 登陆画面改成Character : /etc/inittab的id:x:initdefault:这行改成id:3:initdefault: C. 修改登陆画面 - /etc/issue D. 修改系统日期 date -s "130508" E. BIOS/Security(CPU)/VT 支持64位 | SPC | 1. 打印机/Daemon/Address/TAX/Invoice Status Code /Business Relation/SAF 等 2. Entity/Sub-Account,CostCenter,Project GL Account 等 3. SE版本数据设定 Site/item/BOM 等 4. 包含以下内容 PO=>Supplier Invoice => Matching SO=>Customer Invoice=>Payment Openning Balance Upload WO Flow Finiancel/JE | 完成 | 1
1.1 | 概述 | 名词解释 |  | TC = Transaction Currency BC = Basic Currency SC = Stautory Currency Operational => 旧系统程序 BR = Business Relation => Address Master SI = Supplier Invoice CI = Customer Invoice Layer = 财务层次 Shared Set = 同一数据库共享COA Profile = 同一数据库,定义不同模块科目.例如Sales |  |  |  | 完成
2 | 概述 | 资料来源 |  | 1. QAD Doc : Implementation_TG_v2010EE.pdf 2. QAD Doc : 03 Financials_UG_v2010_EE_All财务.pdf 3. XLS Upload Sample => AttachmentFile Directory 4. VMWare :BaseSetupDB 5. SamSong-Implementation.xlsx - Main 清单 - 静态数据设置顺序 - Attachment 附件 - 动态(参考,未测试) - AccountSample - DayBook Sample 6. /home/mfg/callmenu |  |  |  | 完成
3 | 概述 | 数据导入方法 | CIM - XML Daemon - currency excel integration | 1.导入数据方法 - CIM => 旧版本分销/制造 - XML=> 所有财务EE功能 - XLS => 部分EE功能 2.XML 导入 - Dump XML ?? 如何使用？如何生成? 3.Excel Integration - 不能导入excel,安装excel ".NET Programmability support" 控件 | 2.1 XML Daemon 文件/目录 xsd功能 cp /qad/2010ee/mfgpro/fin/111111 /qad/2010ee/qxtend/demo/qxoser ver/boXML/QADEE/111111.xml (货币修改导出到111111) /qad/2010ee/qxtend/demo/qxoserver/boXML/QADEE(API函数存放在该目录) 2.2 XML Daemon Monitor 2.3 系统搬移作用比较大 2.4 调用Qxtend 的功能 3. GL Account / Customer /Supplier QAD 2008 不支持Offoice 2010 QAD 2011 支持 Offoice 2010 |  | 3.1 控制面版=>卸栽/安装程序=>原则Excel=> .NET Programmability support 3.2 EXCEL2010不支持QAD2008EE | 完成
4 | Sys-Wide | XML 设置 | XML Daemon Configure/Start | Input Directory for XML File : 存在于xsd/API 目录 - 如果存在 Product/Demo DB ,如何导入XML.出错?? |  |  | /app/mfgpro/qxtend/demo/qxoserver/boXML/QADEE | 待测
5 | Sys-Wide | 打印机设定 Printer Setup | 36.13.2 | 1. PAGE : Scroll Output = Yes , Dev Pathname = BLANK 2. Printer : Scroll Output = Yes , Dev Pathname = printer ** 以上设定仅仅使用于SE 程序 ** 所有EE 报表/Brower 打印使用Windows 打印机 | 2. Dev Pathname = Printer 不能修改哦 Initialize Ctrl: text |  | Purchase Order Print 如何打印?? | ok
6 | Sys-Wide | Exchange Rate 类型 Exchange Rate Type | 26.3.1 | 1. Accounting 系统设置的,不能修改 2. Revalution 月末重估时使用 每月月底 3. Inventory 跟库存相关的兑换率 4. Buget 兑换率 5.statutory 法定 优先顺序: Inventory => Statutory=>Statutory'Fallback Accounting Revalution=>Statutory=>Statutory'Fallback Accounting | * System-Owned : 不能修改,系统预设的 * Fallback to ACCOUNT : 如果其他TYPE没有找到,就使用ACCOUNT *Use Validity End Date / Default Validity -和Fallback to Account 冲突 -不知道如何使用?? 从有效日期开始 |  | 业务：用不同Exchange Rate Inventory/Revaluation Inventory Rate = BC & SC 之间的对换 例子: 1/1 - 1/30 月初 Rate 1/31 输入Revaluation 重新评估!
7 | Sys-Wide | 圆整办法 Rounding Method |  |  | ** 注意 4舍5入 明细/汇总不一致! ** 成本小数点N,财务小数点2位
8 | Sys-Wide | 货币维护 Currency | 26.1.1 | 1. 可使用XML进行导出/导入 2. Exchange Rate Profile/Loss 不分货币！！ | 多选 修改 覆盖
9 | Sys-Wide | 系统维护 | 36.24.3.1 | 设置管理货币SC,一个DB只能有一个System Maintain -BR by Domain BR 是否只在目前的domain使用 | 一般不用进行修改
10 | Sys-Wide | Alternate Code（country Main） Country Code Main User Maintenance | 36.2.13 2.14.1 36.3.1 | 1. Field Name = ctry_code1 2. 2.14.1 调用 Alternate Code 3. 用户维护User Maintain 使用 2.14.1 | 36.1.3.1.2 使用国家代码不同哦 ** 36.2.13 COPY FROM System Domain During Domain Setup Complete
11 | Sys-Wide | State County | 36.1.3.2.3 36.1.3.3.3 | 使用excel integration | 附件:36.1.3.2.3-State.xls * ID 可以重复，系统自动调整 * 校验Sheet * 不会删除哦! * 不能多选.
12 | Sys-Wide | VAT 1. Tax Type Maintenance 2. Tax Class Maintenance 3. Tax Usage Maintenance 4. Tax Base Maintenance 5.Tax Environment Maintenance 6. Tax Rate Maintenance (最后设置) | 1) 29.1.1 2) 29.1.5 3) 29.1.9 4) 29.1.13 5) 29.3.1 6) 29.4.1 29.24 Control File | 1. VAT/NON-TAX 2. VAT 3. P17/S13 4. VAT 5. CN From CN To Blank From Blank To CN Tax Type = VAT/NON-TAX 6. VAT P17: Percent Recoverable = 100% Accrue Tax at Receipt = False S17: Percent Recoverable = 0% | 6. 有科目的设定,推迟到后面 3. 使用Usage进行区分，其他的都是VAT
13 | Sys-Wide | Invoice Status Code 供应商发票 | 36.1.11.1 | 1. NOT PO: * Lock Payment 是否可以付款 * Invoice Approve 是否Approved * Allocation Status 是否3单匹配 * Init Status 初始 * Recerver Matching : 是否已经Matching * Status After Maching : Matching后转化成XX状态 2. PO : Receiver Matching = 有采购单时才可以 | 2. 当 Allocation Status = No Allocation Receiver Matching = yes 时,可以更新 Status After Matching SI/CI Status 在同一地方维护！ |  | 1. INIT =>OK2PAY 2. RM-INIT => RM-OK2PAY
14 | Sys-Wide | Credit Terms | 36.1.10.3 | 1. Payment Type : Normal (单个到期日)/ Staged(按阶段收款) 2. 客户/供应商,都使用同一套 | -Staged 时,引用旧Credit Terms 28.17.9 Supplier Aging Analysis Current
15 | Sys-Wide | Business relation Business Relation Autonumber | 36.1.4.3.1 | ** 地址簿 关联 新旧Address Insert a New Row 1. Address Type : Headoffice 2. City/CN/SH 都要输入哦 TAX information 1. Default To Transaction 2. Intercompany Code 3. Customer/Supplier Compensation Allowed 如果是供应商/客户 选择 Internal entity = YES ,可以使用在Entity 维护上 | Intercompany Code. When Intercompany is selected, you must enter an intercompany code. This code is linked to GL accounts and GL transactions for this business relation when an intercompany transaction is created |  | B21701 B21901
16 | Sys-Wide | Shared Set （COA） Shared Set Merge | 36.1.1.3.3 36.25.91 4+3(Mask)+2+2 = 11 | Mask 进行合并科目/子科目/成本中心 组合 - Cost Center / Sub-Acount / Project - 如果不共享的话,独立建立一套 | Shared Set Merge (36.25.91) 在不同Domain进行合并 Source Shared Set : 21901 (TO) Target Shared Set : 21701 (From) COPY 21701 to 2190 * 有 Shared Services Domain lic 才可以Active 多个Domain * 相同的本位币使用同一套Account才有意义 - 如何导出/再导入 ** 使用View条件 - 如何剔除个别数据 ** 多选 |  | Shared Set By Module 21701* => 单独 21702* => 单独 SampleData: 36.1.1.3.3-SharedSet21701.xml
17 | Sys-Wide | GL Layer | 25.8.14.3 | official - 正式层次 ** (Primary 固定） transient - 临时 - Trans-Approve 等待Approve JE - Trans-Template 模板 - Trans-Memo Memo management - 管理 DayBook => Transient , 放入临时层,更新Transient的余额 DayBook=> Official , 立即更新科目余额 | -不同层次之间可以转换 -出报表可以合并 - transient 可选 • Consolidation • Journal entries • Reversing entries (回滚交易) • Matching postings for supplier invoices (暂估AP) |  | PAGE 164
18 | Sys-Wide | SAF Concept | 25.3.7.1.3 | - System Default SAF Concept 7 个是系统固定的 | Attachment File
19 | Sys-Wide | SAF Code | 25.3.7.2 | 默认的数值定义 21701*/21901* | Excel Intergrate 一个不对全部不导入 |  | 25.3.7.2-SAF Code - Debug.xlsx
20 | Sys-Wide | SAF Structure | 25.3.7.4.3 | 定义结构 Site/Manufacturing/Purchase/Sales - 关联于Account/Sub-Account/CC - 最多可以定义5个 Concept | 定义SAF Concept & Default Code 21701Sales / 21701Travel |  | 25.3.7.4.3-SAF Structure.xlsx
21 | Sys-Wide | Domain Create | 36.1.1.1 36.3.4 | 1.本位货币 2.法定货币 Staturory Currency Enabled COA Mask 如何 使用 A. 一般初始化系统时 COA Element without Mask B. 系统设置完成后才有效 -Exclude from Posting:If you select this value, COA elements that are not assigned a COA mask are excluded from use in postings. - No Posting Restrictions: If you select this value, COA elements that are not assigned a COA mask can be used in any posting. 3.公司之间的往来科目?? A. 科目的类型为：Cross-company B. 仅仅为科目,不能有成本中心/项目等 C. 后补 | 1. Code-Page CH : CP936 TW: CP950 2. Active = No , 设置完参数后,Active = Yes 3. Active = yes 时,务必启动 Replication daemon （PAGE 50） 4. Primary Entity 后补 5. Setup Complete = YES,以后就不能修改Shared Set ** 系统设置完成后. Invoice 不能重复/显示SI after SAVE |  | D21701/D21901 Domain User Domain/Entity Access Maintain 设定权限Entity Entity can not modify | 待测
22 | Sys-Wide | Entity Create | 36.1.1.2 | 1. Entity 新增后不能删除. 注意***** 2. BR 中的 internal = yes 时,才可以选择 3. 有交易了,Active 就不能变成No了 4. Domain Active = Yes 才可以进行选择 , 不要选择System Domain 5.Check Budgets on Overlap 预算制定时,相同区间预算数据是否重复(Acc&SubAcc&Cost&Proj&SAF),系统提醒 6.P&L 重估 是否在下个月回写. - QAD SE 版本的GL回滚功能 - QAD SE 版本都是每个月计算,过帐，下个月计算差额 7.Consolidation Entity 是否为合并Entity - 合并Entity PAGE 645 8. AP and AR Exchange Tolerance % - 在进行AR/AP 收付款时,Realized exchange gain or loss 是否超过 %，错误提醒不给通过,数据防错. - 0 表示不检查，稽核! 9.Supplier/Customer Compensation Allowed , 进行AP/AR抵消 10. Additional GL Numbering Tab - 系统自动产生另外一套Numbering , 不是 DayBook 哦 - 000000001 （9 Digits） for Official Layer ONLY - Source Numbering Entity : 用相同一套No ,同一Domain | 6.待测试 Reverse P&L Revaluations. Indicate if revaluation amounts of profit and loss accounts (income and expense accounts) should be reversed at the beginning of the next GL period. 11. Invoice Upper Limit 使用在金税软件中,规定发票的最高发票金额! ENTITY 不能修改： 1.进到其他域在Role Membership Main 将用户与ENTYTY 的Link全部钩上 2.重新登陆,进到自己的域修改 |  | E21701/E21901 Entity 6. Reverse P&L Revaluations = YES 3月 100 USD @6.1 = 610 3月底 100 USD@6.2 = 620 3月收益 10 CNY 4月初 -10 CNY 4月底 100 USD @ 6.3 = 630 630 - 610 = 20CNY 20(4月末-初始Rate) - 10(4月初) = 10 Reverse P&L Revaluations = NO 跟之前一样!
23 | Sys-Wide | Role Create User Maintenance User Domain/Entity Access Role Membership Maintain Role Permissions Maintain | 36.3.6.1 36.3.1 36.3.4 36.3.6.6 36.3.6.5 | 必须指定 36.3.4 后,才运行 36.3.6.6 | 加入用户后,必须跑：User Domain/Entity Access
40 | Domain | Global Tax Control | 29.24 | Accrue Tax at Receipt = No
40.1 | Domain | Bank Payment Format Link | 25.11.2 | 定义公司内部银行类别,跟付/收款流程有关系！ - Supplier/Customer Create 设定银行科目&公司帐号对应 - Customer Payment Status View (27.6.2.3) 使用Payment Instr - Supplier Payment Status View (28.9.1.1.3) 使用Payment Instr
41 | Domain | Company Address | 2.12 | Call BR Entity 217 |  |  | S217 Call B217 B217 / B219
42 | Domain | Account Create | 25.3.13.1 | 1.GL Type <<下面进行解释>> 2. Referenced 系统控制栏位,如果被使用,系统自动=YES 3. In Posting 系统控制栏位,如果科目被过帐，系统自动=YES 4. System Type : PO Receipt .Unapprove Invoice 等 5. Category : Asset/Liability/Expense/Income 5.1 Dudget Group : B/S & P/L 位置 6. Posting - BS/P&L 系统自动带出 (非Standard Account) - DR/CR 系统自动带出(非Standard Account) - Auto/Manul : 该科目可否在JL进行调整(有交易就不能改) 可以调整的有:Bank/Cash/Cross-company/Fixed Asset Open Items/Standard/Tax | PAGE 98 Intercompany |  | DOMAIN Account
42 | Domain | Account Create | 25.3.13.1 | 7. Intercompany - Intercompany Account = Yes, Account Type = Cross-Company Control Account, - Fixed Intercompay / Default Intercompany(EntityGourp) 8. Quantiy / Unit Of Measure JL 输入时,跳出Quantity 进行录入 9. Base Currency Only =YES,只能使用本位币,少用 9.1 Currency Code = USD 一般使用在Bank/Cash Account/AR/P 10.TC Revaluation in BC =>外币转移到本币使用Rate Type TC Revaluation in SC =>外币转移到法定使用Rate Type Rate Type for Revaluation in BC * User Defined Rate 有用 Rate Type for Revaluation in SC * User Defined Rate 有用
42 | Domain | Account Create | 25.3.13.1 | 11.Analysis Type - Both : CostCenter/Project/SAF 可选择使用Sub-Account Profile - CostCenter : CostCenter/SAF 可选择使用Sub-Account Profile - None: 可选择使用Sub-Account Profile - Project : Project/SAF 可选择使用Sub-Account Profile 12. Analysis Type = Both - At Least One 最少输入1个 CostCenter & Project - Both Required 2个都需要 -Excluding each Other: You must specify either a project or a cost center on the transaction. - GL Analysis Set On Date / By 谁设定/设定日期 12.5 Banking Daybook Profile ( 使用 31.1.1)
42 | Domain | Account Create | 25.3.13.1 14+10 = 24 类 | sub-Account Mask Code 指定 指定,哪个Sub-Account 使用对应的Sub-Account Mask - 必须启动Domain 的选项! | M.System Account -Unrealiz/Relizaed Exchange Grain/Loss - Rounding - PO Receipt Account - Result of the Current Year - Result of Previous Years - Unmatched Invoices (中间AP科目,一个系统用一个科目) 科目组合参考-总结 - 系统科目 *只有PO Receipt 才可以使用 CostCenter/Project/SAF,其他只能 使用SubAccount - 非系统科目 * TAX/Bank/ClosingAccount 只能使用Sub *Cross-Company 只能使用ACCOUNT * Supplier/Customer Control Account 不能使用SAF * 其他的非系统科目都可以使用 |  | 25.3.13.1-GL Account DomainAllAccount
43 | Domain | Sub-Account Mask | 25.3.9.1.3 |  |  |  | Elec - From 7000101 To 7000101 Braking
44 | Domain | Sub-account activities Link Mask | 25.3.17 | Sub-Account Mask Code 指定 指定,哪个Sub-Account 使用对应的Sub-Account Mask - 必须启动Domain 的选项! | Elec Braking |  | Elec Braking
45 | Domain | Cost Center Mask Cost Center Create | 25.3.9.2.2 25.3.20.1 | -Cost Center Administrator. 系统用户 - Cost Center Link Mask - Retrieve SAF Structure from GL * GL Account 统一进行设定. AnalysisType : CostCenter & Both 时,指定SAF | Admin
46 | Domain | Project Group Project Status Create Project Create Project Mask Modify | 25.3.11.6.3 25.3.11.7.1 25.3.11.1.1 25.3.9.3.2 |  | Project Status: - Initial =>可以在Operation (例如下PO等), 不能使用在Account 上 - Open => 可以Operation & Account - Closed for Accounting: A project with this status cannot be used in posting costs(成本) or revenue(收入), -Closed for Costs: A project with this status cannot have expenses(费用) posted to it. -Closed: Projects with this status cannot be used in transactions. |  | Initial Open Close
47 | Domain | Exchange Rate Create Exchange Rate Derive(派生) | 26.4.1 26.4.5 | Inventory Exchange Rate : statutory currency and base currency | -9999/12/31 为最大 - To Date 是不能维护的 |  | 26.4.1-Exchange Rate Create.xlsx Entity A (CNY): 1USD = 6.3CNY 1CNY = 1.2HKD Entity B (HKD) Derived Result 1USD = 8.2HKD 计算的结果
48 | Domain | GL Correction Control | 25.13.24 | GL Correction = Yes 财务分录,可以产生负数 ** 需要额外定义对应的Daybook GL Summarization 正负数分开进行过帐！ | Produce correction transactions for invoices generated as a result of sales orders for a total negative amount, such as credit notes. |  | 例如: **计划外入库 Qty=10 STD = 20 Debits Inventory $200 Credits Purchases $200 ** 实际只有 Qty = 9 个,调整-1 方法一:(Correction = NO) Credits Inventory $20 Debits Purchases $20 方法二: (Correction = YES) Debits Inventory $-20 Credits Purchases $-20
49 | Domain | Account control | 36.9.24 | YES, 输入默认值. - 之前的36.1 |  |  | 输入都无效?? 没有启动-Replication Daemon
50 | Domain | GL Op Transaction Control | 36.9.13 | ** Inventory Transaction Posted = Yes 表示不能删除GL Transaction ** 建议先不要选择,系统上线后在选择! | GL Transaction Delete/Archive (36.23.2)
51 | Domain | Domain Modify | 36.1.1.1.2 | Complete = Yes Cross-Company Account | 以下数据不能再修改 Shared Set Entity Base Currency
51 | Domain | TAX Box TAX Group | 29.6.1.1.1 29.6.1.2.3 |  |  |  | 217Box 217TaxG
52 | Domain | VAT 1. Tax Type Maintenance 2. Tax Class Maintenance 3. Tax Usage Maintenance 4. Tax Base Maintenance 5.Tax Environment Maintenance 6. Tax Rate Maintenance | 1) 29.1.1 2) 29.1.5 3) 29.1.9 4) 29.1.13 5) 29.3.1 6) 29.4.1 | 1. VAT/NON-TAX 2. VAT 3. S17/S13/S0 (P17/P13/P00) 4. VAT 5. VAT From CN To Blank From Blank To CN Tax Type = IN/OUT/NON-TAX 6. VAT P17: Percent Recoverable = 100% Accrue Tax at Receipt = False S17: Percent Recoverable = 0% | 6. 有科目的设定,推迟到后面 使用Usage进行区分，其他的都是VAT
53 | Domain | DayBook Maintenance | 25.8.1.1 | 1. 所有库存交易DayBook 类型为:JE , Operational 2. AR 类型为 Operational | 参考Sheet "DayBook" - Revalued 必须单独导入** - |  | PAGE 170 25.8.1.1-Daybook Create.xlsx
54 | Domain | Default DayBook Maintenance 可以By Site | 25.8.4 | Inventory Daybook DayBook Type : Journal Entries Control : Operational IC/SO/WO Layer : Official | *25.13.24 设定是否使用 correction daybook *Tran Type = BLANK 为系统Daybook
54.5 | Domain | Daybook Set Maintenance | 25.8.7 | ** AR 的都是 Operational Type 理由: 通过SO过帐 ** AP 的都为 Finiancal Type 理由: 直接在财务模块录入 ** Sales Order Accounting Control (36.9.6)设置 * Use Correction Invoice (负数发票) * Default Daybook Set * Use Daybook Set By Site ** GL Correction Control （25.13.24）设置
55 | Domain | Bank Account Maintenance | 25.3.13.1 | ** Address & Account no 收款/付款 时候使用,很重要 ** 定义Banking Daybook Profile | ** 一定要使用Profile ** AP/AR Disc Account (STD Account) |  | Sample :116001 CNY 加入Address
55.5 | Domain | Profile Create | 36.1.1.4.1 | ** Banking Profile =>DayBook ** Cash (Paid/Receiver)Profile => DayBook ** Customer Account Profile (AR) => Account ** Sales Profile (Sales Income) => Account ** Prepayment Profile => Account ** Supplier Account Frofile (AP) => Account ** Expense Profile (Expense Account ) => Account | 基于Shared Set 进行设定 |  | Prepayment (AR/AP )Profile Credit Note Profile Invoice Profile Sales/Expense Profile
56 | Domain | Domain GL Period Create | 25.4.1.1 | 2013/2014 Year
57 | Domain | Tax Period Create | 25.4.4.1 | 一般都相同！
58 | Domain | Customer Payment Status View | 27.6.2.3 | ** 一般设置PAID就OK了 ** Payment Instrument 很重要！ ** 跟客户对应的Bank & Own Bank 关联 |  |  |  | 待试
59 | Domain | Supplier Payment Status View | 28.9.1.1.3 | ** Payment Instrument 很重要！ ** 跟供应商对应的Bank & Own Bank 关联 | Init/For Collection/Paid
60 | Domain | Customer Create | 27.20.1.2 | - 1. Customer1-36.1.4.3.1-BR.xlsx - 2. Customer2-27.20.1.5-CustomerFIN.xlsx - 3. Customer3-02.01.01-CustomerData.xls - 4. Customer4-2.1.1.txt | Profile Create - AR Profile 21CAR - Cust Acc Profile - Sales Profile 21SAP - Cust Sales Profile |  | 1.1 Address Name 1.2 TAX Information 2.1 BR 设置 36.1.10.3 2.2 Profile AR/Sales 2.3 Invoice Status Code 2.4 Currency 2.5 Banking No 217&Customer 对应 3.1 Default Site 3.2 Class 3.3 Daybook Set :21701Sal
61 | Domain | Customer Ship-To | 27.20.2.5 | 可以关联其他客户数据 - 不能修改!!!!
62 | Domain | Supplier Type | 28.20.2.1
63 | Domain | Supplier |  | - 1. Supplier1-36.1.4.3.1-BR - 2. Supplier2-28.20.1.5-SupplierFIN.xls - 3. Supplier3-02.03.01-SupplierData | Profile Create - AP Profile 21UAP - Supplier Acc Profile - Pur Profile 21PAP - Pur Account Profile |  | 1.1 Address Name 1.2 TAX Information 2.1 BR 设置 36.1.10.3 2.2 Profile AP/Purchase 2.3 Invoice Status Code 2.4 Currency 2.5 Banking No 217&Customer 对应 3.1 Default Site 3.2 Class 3.3 Daybook Set :21701Pur
64 | Domain | 1. Inventory Status Report 2. Site Maintnance 3. Location 4. Inventory Control 5. Product Line 6.Trailer Code Maintenance 7.Sales Order Control 8.Sales Order Accounting Control 9. Generalized Code 10.Item Status 11. Item Data 12. Cost Set Maintenance(30.1) | 1.1.1 1.1.13 | 2.1. Domain/Entity Vari Account : 6820101 STANDARD Account 4.1. Default Site => S21701 Reason Type "ESIG" 8.1 Use Daybook Set By Site 8.2 21701Sal (Daybook Set) 8.3 Use Correction Invoices 销售订单录入时，可输入调整INV 9. pt_um/pt_promo/pt_part_type/pt_group/pt_abc/pt_size_um 12 支持Period Cost Method (AVG/FIFO/LIFO) (30.5.24 - Enable PC) | Sale Order Accounting Control : •Define the company address to appear on printed sales order documents • Specify whether all sales order line items or only lines with non-zero quantity to invoice should print on invoices • Specify whether to base daybook defaulting and validation on site-specific setup records • Indicate whether to use correction invoices. When activated, additional fields display in Sales Order Maintenance that let you create a correction sales order for an original invoice. |  | YYY S21701
65 | Domain | 1. Purchasing Accounting Control 2.Supplier Invoice Control | 36.9.5 28.24 | 1.1 - Use Daybook Set By Site 1.2 - Default Daybook Set: 2.1 Batch For ERS Only 2.2 Invoice Open Qty/Amt (Receiver Matching Create) 默认 2.3 Use Expensed Item Var Accts. (Attachment File) 2.4 Hold Variance Amount. 3单匹配产生不利差异时，余额转入Hold Amt
66 | Domain | Work Order Setup 1. Work Order Control 2. Product structure Main 3. Department Maintenance 4. Work Center Maintenance 5.Calendar maintenance 6.Standard Operation Maintenance 7.Routing Maintenance 8.Routing Cost Roll-Up 9. Product Structure cost roll-up 10. Product Structure Cost Report 11.Daybook For WO 12. Number Range Maintenance | 36.9.11 13.5 14.1 14.5 36.2.5 14.9 14.13.1 14.13.13 13.12.13 20*2 + 2 + 1 = 43 CNY 25.8.1.3 | 1.1 Post variances at SFC 2.1 界面完全不同了 2.2 自动生成BOM Code 4.1 Auto-Firm => 在Planning and Scheduling Workbenches 使用 | 1.1 Post variances at SFC Yes: Labor and burden variances are calculated and posted whenever shop floor labor feedback transactions are entered. • No: Variances are suppressed and not calculated or posted until the work order is received. Setting the field to No reduces the number of variance transactions posted to the general ledger, particularly if there are many shop floor labor transactions processed before material receipts are recorded. |  | 2. 21701-FG01 3. 217Dep01 11. Daybook Type = Journal Entries WOCLOSE WOISS WOMVAR WORCT
67 | Domain | TESTING ( Purchase ) |  | 1. Purchase Order Maintenance (5.7) - 2. Purchase Order Receipts (5.13.1) 3. Unposted Transaction Register (25.13.14) 4. Operational Transaction Post (25.13.7) 5. Journal Entry View (25.13.1.3) 6. Supplier Invoice Create (28.1.1.1) 7. Supplier Invoice View (28.1.1.3) 8. Receiver Matching Create (28.2.1) 9. Supplier Invoice View (28.1.1.3) 10. GL TC Balance Inquiry (25.15.2.8) | 6.1 Expense OK2Pay 6.2 AP Matching RM-INIT =>OK2PAY - Operational Module 必须使用25.13.7 进行POST,直接进入OFFICIANL LAYER - FIN 的不用POST |  | 1. PO217002 17%VAT 1000@10 2. 10 @ 10 = 100 Receipt:RC1000 3. PPV & PO Receipt & Inventory 4. POST 5. Jornal entry View 费用AP:2013 / SINV / 000000001 SI Posting: CR: 200001 AP Account DR: 250001 UnApprove Invoice Matching Posting CR: 250001 UnApprove Invoice DR: 6600101 Expense Account 匹配AP:2013 / SINV / 000000003 SI Posting: CR: 200001 AP Account DR: 140001 AP TAX DR: 250001 UnApprove Invoice Matching Posting CR: 250001 UnApprove Invoice DR: 252001 PO Receipt 价格差异: 2013/SINV/000000004 SI Posting: CR: 200001 AP Account DR: 140001 AP TAX DR: 250001 UnApprove Invoice Matching Posting CR: 250001 UnApprove Invoice C/DR: 6740101 VAR DR: 252001 PO Receipt
68 | Domain | TESTING Sales =>AR |  | 1. Sales Order Maintenance (7.1.1) 2. Sales Order Shipments (7.9.15) 3. Unposted Transaction Register (25.13.14) 4. Operational Transaction Post (25.13.7) 5. Journal Entry View (25.13.1.3) 6. Preview Invoice Print (7.13.3) 7. Invoice Post and Print (7.13.4) 8. Customer Invoice View (27.1.1.3) | 1.1 Original Invoice / Original Number 36.9.6 Use Correction Invoices: 1.2 DayBookSet Default from Customer 1.3 AR Account取消了 2.1 加入了Document No 2.2 Print Invoice 等选项取消了 6.1 Print Invoice 不会产生Invoice NO# 6.2 查看而已！ 7.1 产生发票号码 7.2 直接更新Account Balance 7.3 产生JL&Customer INV |  | 1. SO217001 10000@10 17% 2. 10 Qty 3. GL Transaction CR : Inventory 150001 DR: COGS (Material / Labor/Burden) 5X00101 7. DR: 130001 2013/INV000000001 AP CR: 240001 2013/CINV000000001 TAX CR: 4000101 2013/CINV000000001 Income
69 | Domain | TESTING Opening Balance Upload 系统上线时进行导入 |  | 1. Customer Opening Balance Create (27.1.10) 2. Supplier Opening Balance Create (28.1.15) 3. Customer Invoice View (27.1.1.3) 4. Supplier Invoice View (28.1.1.3) | 1. Customer Opening Balance * 使用的Daybook,不能为Opernational * 必须手工进行调整/再调整回来 2. Supplier Openning Balance * 使用DayBookSet 对应Daybook为Fin * 注意兑换率(TC&BC&SC) |  | 1. Account 1670101 Transfer Clearing DR: AR Account 130001 CR: Transfter Clearing Account1670101 2. 建立特别的DayBook 3. 注意由于ExchangeRate不同导致的Balance <> Zero 4. 供应商必须使用之前的Daybook
70 | Domain | TEST Customer Invoice Supplier Invoice |  | 1. Customer Invoice Create (27.1.1.1) Customer Invoice View (27.1.1.3) 2. Supplier Invoice Create (28.1.1.1) Customer Invoice View (28.1.1.3) | 1.1 Invoice Type : Invoice / Credit Note 必须为正数,Correction 必须为负数,归属 不同的DayBook * 使用了Credit Note 就不使用Correction * DayBook Type is "FINANCIAL" 1.2. 输入CI Posting Account 1.3 Descption POST to GL 2.1 Refence 必须输入，描述重新复位 2.2.使用Supplier的默认DaybookSet
71 | Domain | TESTING Open Item Adjustment |  | Open Item Adjustment Create (25.13.5) Open Item Adjustment View (25.13.6) Journal Entry View |  |  | - Allocation Account (过渡科目) - 用于清除目前AR/AP 余额
72 | Domain | TEST Customer Payment |  | Customer Payment Create (27.6.4.1) Customer Payment Modify to Initial(27.6.4.12) Customer Payment Modify to Allocated(27.6.4.13) Customer Payment Modify to Accepted(27.6.4.14) Customer Payment Status Create(27.6.2.1) Customer Bank Journal Entry View | Status: init : 没有任何GL产生,不关联INV Allocation : 产生GL,关联INV,PrePayment Accept : PIP (138001)转入Bank
73 | Domain | TEST Supplier Payment |  | Single Flow - 1. Supplier Payment Create to Initial (28.9.3.8) - 2. Supplier Payment Modify to Allocated (28.9.3.13) - 3. Journal Entry View (25.13.1.3) - 4. Supplier Payment Modify to Accepted（28.9.3.14） - 5. GL TC Balance View ( 25.15.2.8) | 1. 不生成任何GL分录,不关联SI 2. 生成GL,关联SI 收款中间过度科目:208001 2013/000000001 DR AP Prepayment 14CNY DR AP 9CNY CR PIP 208001 23CNY 4. DR PIP 208001 23CNY CR Bank 23CNY
74 | Domain | TEST Supplier Payment -Selection |  | 1. Supplier Payment Selection Create (28.9.4.1) 2. Supplier Payment Selection Confirm (28.9.4.5) 3. Supplier Payment Selection Detail Print (28.9.9.7 ) ** 4. Supplier Check Print (28.9.9.3) ** 5. Supplier Payment View (28.9.3.3) 6. Supplier Activity Dashboard (28.18.1) 7. GL TC Balance View ( 25.15.2.8) | 1. Status : Init 不产生GL 2. 产生GL,Status is Confirm DR: AP Account 200001 CR: PIP 208001 3. 安装 Crystal Report ,否则不能运行 4. 不能运行 5. Supplier Payment View to PAID CR: 116001 DR: PIP 208001 |  | 1. SupplierPaySel#00001
75 | Domain | TEST Work Order Module |  | 1. Unplanned Receipts (3.9) 2. Inventory Detail (3.3) 3. WO Maintenance (16.1) 4. WO Release (16.6) 5. WO Browse (16.2) 6. WO Component Issue (16.10) 7. WO Receipt (16.11) 8. WO Accounting Close (16.21) 9. Unposted Transaction Register (25.13.14) 10. Operational Transaction Post (25.13.7) | 多了一个单号: 1. WO发料单号 2. WO成品入库单
76 | Domain | TEST Journal Entry Create |  | Journal Entry Create (25.13.1.1) Journal Entry View (25.13.1.3) Journal Entry Excel Integration (25.13.1.6) ** 没有测试通过** Mass Layer Transfer Execute (25.13.11) **转换Layer | 1. Create Normal JE - Account Code:7000101 - 7000102 Travel Expense SAF (Sample) * Employee * Purpose * Car Registration 2. Template - Save as Template = yes - Template Code = Template0001 - Template DR/CR Amt %%%% - New JE , and Call Template - TOTAL Amt 3. Reversal = Yes ,OriginalPostingRef <>Blank 4. 直接修改Layer & Mass Layer Transfer
77 | Domain | TEST Banking Entry |  | Banking Entry Create (31.1.1) Banking Entry View (31.1.3) Banking Entry Allocate (31.1.5) | Attachment File |  | 152 CNY 为其他收款 230 CNY 为银行 66 CNY 为预收款 12 CNY 为冲SI

## Implementation静态
组别 | 步骤 | 菜单 | 标题 | 中文 | 方法 | 必须 | 备注
SYS | 1010 | 36.14.16.6.1/4 | XML Daemon Configure | XML Daemon配置 | 手工 | Y | ‘- /qad/2010ee/qxtend/demo/qxoserver/boXML/QADEE 存放xsd文件哦
SYS | 1020 | 36.13.2 | Printer Setup Maintenance | 打印机设置维护 | 手工 | Y | 1. PAGE : Scroll Output = Yes , Dev Pathname = BLANK 2. Printer : Scroll Output = Yes , Dev Pathname = printer
SYS | 1021 | 36.13.4 | Printer Default Maintenance | 打印机默认维护 | 手工 | N
SYS | 1030 | 26.3.1 | Exchange Rate Type Create | 汇率类型创建 | 手工 | N | 默认已经存在,ACCOUNT,REVAL
SYS | 1040 | 26.2.1 | Rounding Method Create | 取整方法创建 | 手工 | N
SYS | 1050 | 26.1.1 | Currency Create | 货币创建 | 手工 | Y
SYS | 1060 | 36.24.3.1 | System Maintain (Set Mgt Curr) | 系统维护 | 手工 | Y | 设置管理货币,每个数据库只能有一个System Maintain
SYS | 1070 | 36.1.3.1.1 | Country Create | 国家创建 | 手工 | Y | 国家
SYS | 1080 | 36.2.13 | For country | 通用代码维护 | 手工 | Y | ctry_code1
SYS | 1090 | 2.14.1 | Country Code Data Maintenance | 国家代码数据维护 | EXCEL | Y
SYS | 1010 | 36.1.3.2.3 | State View/County |  | EXCEL | Y
SYS | 1119 | 29.6.1.2.1 |  | 税组创建
SYS | 1120 | 29.2.1 | Tax Zone Maintenance | 纳税区域维护 | 手工 | Y | Sample : CN
SYS | 1130 | 29.1.1 | Tax Type Maintenance | 税类型维护 | 手工 | Y | Sample : IN/OUT/NON-TAX
SYS | 1140 | 29.1.5 | Tax Class Maintenance | 税收类别维护 | 手工 | Y | Sample : VAT
SYS |  | 29.1.9 |  | 税用途维护 | 手工 | Y | Sample : 17/13/0
SYS | 1160 | 29.3.1 | Tax Environment Maintenance | 纳税环境维护 | 手工 | Y | Sample : CN From CN To Blank From Blank To CN
SYS |  | 29.4.1 |  | 税率维护 | 手工 | Y | Sample : IN: Percent Recoverable = 100% Accrue Tax at Receipt = False OUT: Percent Recoverable = 0%
SYS | 1180 | 36.1.11.1 | Invoice Status Code Create | 发票状态代码创建
SYS | 1190 | 36.1.10.1 | Credit Terms Create | 支付方式创建 |  |  | For those used in supplier & customer.
SYS | 1200 | 36.1.4.3.1 | Business Relation Create (For Entity) | 业务关系创建 |  |  | Entity only
SYS | 1210 | 36.1.1.3.1 | Shared Set Create | 共享集创建 |  |  | DefCustomer
SYS | 1220 | 25.8.14.1 | GL Layer Create | 总帐层创建 |  |  | Primary / DefTransient/DefManagement
SYS | 1230 | 25.3.7.1.1 | SAF Concept Create | SAF概念创建 |  |  | Site
SYS | 1240 | 25.3.7.2.1 | SAF Code Create | SAF代码创建 |  |  | 217/219
SYS | 1250 | 25.3.7.4.1 | SAF Structure Create | SAF结构创建 |  |  | Site
SYS | 2000 | 36.1.1.1.1 | Domain Create | 域创建 |  |  | D217/D219
SYS | 2010 | 36.1.1.2.1 | Entity Create | 会计单位创建 |  |  | E217/E219 Active = Yes / Setup Complete = No
SYS | 2020 | 36.3.6.1 | Role Create | 角色创建
SYS | 2030 | 36.3.6.5 | Role Permissions Maintain | 角色许可维护
SYS | 2040 | 36.3.4 | User Domain/Entity Access Maintain | 用户域/会计单位访问权限维护
SYS | 2050 | 36.3.6.6 | Role Membership Maintain | 角色成员维护
SYS | 2060 | 36.3.1 | User Maintenance | 用户维护
** | 2070 | 25.3.13.1 | GL Account Create (for domain's acct) | GL 帐户创建 |  |  | For Domain Account ONLY
DOM | 2080 | 29.24 | GTM Control | 全球税务管理控制文件
DOM | 2090 | 2.12 | Company Address Maintenance | 公司地址维护 |  |  | S217/S219
DOM | 2100 | 25.3.9.1.1 | Sub-Account Mask Create | 分帐户掩码创建
DOM | 2110 | 25.3.9.2.1 | Cost Center Mask Create | 成本中心掩码创建
DOM | 2120 | 25.3.17.1 | Sub-Account Create | 子帐户创建 |  |  | All
DOM | 2130 | 36.1.1.4.1 | Profile Create (Sub-Acct) | 配置文件创建 |  |  | AB only
DOM | 2140 | 25.3.17.1 | Sub-Account Create (Link Mask) | 子帐户创建
DOM | 2150 | 25.3.20.1 | Cost Center Create | 成本中心创建 |  |  | All
DOM | 2160 | 36.1.1.4.1 | Profile Create (Cost Center) | 配置文件创建 |  |  | TXXX only
DOM | 2170 | 25.3.20.1 | Cost Center Create (Link Mask) | 成本中心创建
DOM | 2180 | 25.3.11.6.1 | Project Group Create | 项目组创建 |  |  | GP01 only
DOM | 2190 | 25.3.11.7.1 | Project Status Create | 项目状态创建 |  |  | Initial, Open & Close
DOM | 2200 | 25.3.11.1.1 | Project Create | 项目创建 |  |  | P001
DOM | 2210 | 36.1.1.4.1 | Profile Create (Project) | 配置文件创建
DOM | 2220 | 26.4.1 | Exchange Rate Create | 汇率创建
DOM | 2230 | 30.17.1 | Cost Element Maintenance | 成本要素维护
DOM | 2240 | 25.3.13.1 | GL Account Create (all accounts) | GL 帐户创建
DOM | 2250 | 36.1.1.4.1 | Profile Create (Account) | 配置文件创建
DOM | 2260 | 25.13.24 | GL Correction Control | 总帐纠正控制 |  |  | YES
DOM | 2270 | 36.9.24 | Domain/Account Control | 域/账户控制
DOM | 2280 | 36.9.13 | GL Op Transaction Control | 总帐Op事务控制
DOM | 2290 | 36.1.1.1.2 | Domain Modify(cross-com. Acct) | 域修改
DOM | 2300 | 29.4.1 | Tax Rate Maintenance
DOM | 2310 | 25.8.1.1 | Daybook Create
DOM | 2320 | 36.1.1.4.1 | Profile Create (Daybook)
DOM | 2330 | 25.8.4 | Default Daybook Maintenance
DOM | 2340 | 25.8.7 | Daybook Set Maintenance
DOM | 2350 | 25.3.13.1 | GL Account (Own Bank Number) |  |  |  | For those used in supplier & customer.
DOM | 2360 | 25.4.1.1 | Domain GL Period Create |  |  |  | 2013
DOM | 2370 | 25.4.4.1 | Tax Period Create |  |  |  | 2012 & 2013
DOM | 2380 | 25.4.5.1 | Budget Report Period Create |  |  |  | 2012 & 2013
DOM | 2390 | 27.6.2.1 | Customer Payment Status Create |  |  |  | For Check, no draft.
DOM | 2400 | 28.9.1.1.1 | Supplier Payment Status Create |  |  |  | For Check, no draft.
DOM | 2410 | 25.11.1 | Payment Format Maintenance |  |  |  | Check-AR, Check-AP
DOM | 2420 | 25.11.2 | Bank Payment Format Link |  |  |  | For those used in supplier & customer.
DOM | 2430 | 27.20.4.1 | Customer Type Create
DOM | 2440 | 36.1.1.4.1 | Profile Create (Customer & Sales Acct.)
DOM | 2450 | 36.1.4.3.1 | Business Relation Create (Customer)
DOM | 2460 | 27.20.1.1 | Customer Create
DOM | 2470 | 27.20.1.9 | Customer Bank Number Import (op.)
DOM | 2480 | 27.20.2.1 | Customer Ship-To Create(op.)
DOM | 2490 | 2.15.1 | Logistics Charge Code Maintenance | Cancel
DOM | 2500 | 2.15.13 | Inbound Account Maintenance | Cancel
DOM | 2510 | 2.15.4 | Terms of Trade Maintenance | Cancel
DOM | 2520 | 2.15.24 | Logistics Accounting Control | Cancel
DOM | 2530 | 28.20.2.1 | Supplier Type Create
DOM | 2540 | 36.1.1.4.1 | Profile Create (Supplier & Pur Acct.)
DOM | 2550 | 36.1.4.3.1 | Business Relation Create (Supplier)
DOM | 2560 | 28.20.1.1 | Supplier Create
DOM | 2570 | 28.20.1.7 | Supplier Bank Number Import (op.)
DOM | 2580 | 1.1.1 | Inventory Status Code Maint |  |  |  | YYY
DOM | 2590 | 1.1.13 | Site Maintenance |  |  |  | 1000 & 2000
DOM | 2600 | 3.24 | Inventory Control
DOM | 2610 | 1.2.1 | Product Line Maintenance (Code only)
DOM | 2620 | 1.2.1 | Product Line Maintenance (with Acct.)
DOM | 2630 | 1.2.5 | Purchasing Account Maintenance
DOM | 2640 | 1.2.13 | Inventory Account Maintenance
DOM | 2650 | 1.2.17 | Sales Account Maintenance
DOM | 2660 | 7.1.24 | Sales Order Control
DOM | 2670 | 5.24 | Puchase Order Cotrol
DOM | 2680 | 36.9.6 | Sales Order Accounting Control
DOM | 2690 | 25.8.10 | Daybook Set by Site Maintenance
DOM | 2700 | 2.1.1 | Customer Data Maintenance
DOM | 2710 | 2.3.1 | Supplier Data Maintenance
DOM | 2720 | 1.4.9 | Item Cost Maintenance
DOM | 2730 | 36.9.2 | Inventory Accounting Control
DOM | 2740 | 36.9.5 | Purchasing Accounting Control
DOM | 2750 | 28.24 | Supplier Invoice Control
DOM | 2760 | 36.9.11 | Work Order Accounting Control
DOM | 2770 | 25.5.1.1 | Budget Create (BS Report Format)
DOM | 2780 | 25.5.1.1 | Budget Create (PL Report Format)
DOM | 2790 | 25.5.2.1 | Budget Group (HQ Account)
DOM | 2800 | 25.13.1.11 | GL Open Item Allocation Key |  |  |  | Discuss in CRP2 process.
DOM | 2810 | 25.19.1.3 | Consolidation Period Cross-Ref Maintain |  |  |  | Discuss in CRP2 process.
DOM | 2820 | 25.3.14.1 | COA Cross Reference Create |  |  |  | Discuss in CRP2 process.
DOM | 2830 | 36.2.13 | G.C. Maint - Sales Channel
DOM | 2840 | 14.1 | Department Maintenance
DOM | 2850 | 14.5 | Work Center Maintenance |  |  |  | Reload on Dec.23, only 2 digits allowed in Rate.
DOM | 2860 | 14.13.13 | Routing Cost Roll-Up |  |  |  | By Leyi.
DOM | 2870 | 13.12.13 | Product Structure Cost Roll-Up |  |  |  | By Leyi after 1.4.17 loading
DOM | 2880 | 32.1.1 | Method Maintenance |  |  |  | By Tony Jan. 7.
DOM | 2890 | 32.1.13 | Fixed Asset Location Maint |  |  |  | By Tony Jan. 7.
DOM | 2900 | 32.1.17 | Class Maintenance |  |  |  | By Tony Jan. 7.
DOM | 2910 | 32.1.9 | Book Maintenance |  |  |  | By Tony Jan. 7.
DOM | 2920 | 32.3 | Fixed Asset Maintenance |  |  |  | By Tony Jan. 7.
Note on C2: Author: Inactive

## Attachment
0 | 图片不见了
4 | XML Daemon Configure/Start
5 | Printer
6 | Exchange Rate 类型
12 | Tax Base Maintenance
用途多个
13 | Invoice Status Code 供应商发票
25.3.7.1.2 | SAF Concept Modify
14 | Credit Term
40 | Global Tax control
42 | Intercompany
Item 46
Item 48
Item 50
54 Default Daybook
56 | Profile
58 | Customer Payment Create
Item 65
66 | BOM
67.3 | 采购收货
44 | Sub-Account Mask
77
Item 18

## 动态
动态数据项目 | 日期 | 时间 | 顺序 | 步骤 | 执行人 | 抽取程序/模板 | 对照表 | 预计需要时间 | 验证方法 | 前提 | 用户准备事项 | 注意事项 | 备注 | 2011-12-05 | [10 empty] | 2011-12-06 | 2011-12-07 | 2011-12-08 | 2011-12-09
[14 empty] | 9am | 10am | 11am | 12pm | 1pm | 2pm | 3pm | 4pm | 5pm | 6pm | 7pm
准备工作 | 2011-12-05 | 9:00-9:30 | 1 | backup
|  |  | 2 | 查看汇率设置
|  |  | 3 | 查看item & inventory status
AP暂估余额 – 非生产性物料 | 2011-12-05 | 9:30-13:00 | 4 | 提取eb2 AP accrual 明细数据 (”M”类型) 提取数据 | Davis | xxpprp06.p (95.3.12) |  | 0.5 | 1． Eb2 95.13.12 与 EE 5.13.10的报告比较，按新旧暂估应付科目小计金额应该一致 (剔除圆整尾差因素)。 | 1． 使用eb2中收货时的历史价格, 历史汇率 2． 保持收货的明细记录 3．现有客户化程序95.3.12，该明细账应与总账accrual科目一致。 | 1． 建议尽快完成发票的匹配工作。 | 1．存在外币订单，如果数量很少，可考虑手工输入。 2.PO号码变化,去掉前一位编吗，保持该编号不与open PO编号冲突。 3． Receiver # 可以变化，张元琼确认11/25 4． Purchase account 科目使用”9999” 5．清理外币收货，尽量全部清理完毕。
|  |  | 5 | 转换为excel文件，转换相关数据：PO#/Recevier #/Account code | Davis |  |  | 0.5
|  |  | 6 | 分别生成PO 和 PO Receiver的cimload 文件 | Roger |  |  | 0.5
|  |  | 7 | 导入PO | Roger |  |  | 1
|  |  | 8 | 导入PO receipt | Roger |  |  | 1
|  |  | 9 | 用户确认 | 张元琼
|  |  | 10 | backup
期末AP暂估余额 – 生产性物料 – 外包类型 | 2011-12-05 | 13:00-15:00 | 11 | 手工建立一特殊累计工单 | Davis |  |  | 0.5 | 1． Eb2 95.13.12 与 EE 5.13.10 的报告比较，按新旧暂估应付科目小计金额应该一致(剔除圆整尾差因素)。 2． EE 5.13.10 各科目小计金额与 GL TB 期初数中的暂付科目一致。 | 1. 使用eb2中收货时的历史价格, 历史汇率 2． 保持收货的明细记录 3．eb2现有客户化程序95.3.12，该明细账应与总账accrual科目一致。 | 1．建议通知供应商尽量开票，完成发票的匹配工作。 2． 现在开始清理应付暂估，如负数的暂估。 | 1． 事先建立一特殊工单, 选一非”S” 类型ITEM，状态为 Closed。工单ID号供所有收货单使用。 2． Cimload格式重新定义。 3． Packing slip & receiver # 处理见下节。 4． 该部分处理产生的COP科目的余额将在GL中reversed 掉。
|  |  | 12 | 使用eb2现有客户化程序xxpprp06.p (95.13.2), 提取eb2 AP accrual 明细数据 (”S”类型) 提取数据 | Davis | xxpprp06.p (95.3.12) |  | 0.5
|  |  | 13 | 转换为excel文件，转换相关数据 | Davis |  |  | 0.5
|  |  | 14 | 生成PO Receiver的cimload 文件 | Roger |  |  | 0.5
|  |  | 15 | 导入PO receipt | Roger |  |  | 0.5
|  |  | 16 | 用户确认
|  |  | 17 | backup
期末AP暂估余额 – 生产性物料 – 非外包类型 | 2011-12-05 | 15:00-22:00 | 18 | 提取eb2 AP accrual 明细数据 (blank类型) 提取数据 | Davis | xxpprp06.p (95.3.12) |  | 0.5 | 1． Eb2 95.3.12 与 EE 5.13.10 的报告比较，按新旧暂估应付科目小计金额应该一致(剔除圆整尾差因素)。 2． EE 5.13.10 各科目小计金额与 GL TB 期初数中的暂付科目一致。 | 1． 使用eb2中收货时的历史价格, 历史汇率 2． 保持收货的明细记录 3． eb2现有客户化程序95.3.12，该明细账应与总账accrual科目一致。 | 1． 建议通知供应商尽量开票，完成发票的匹配工作。 2． 现在开始清理应付暂估，如负数的暂估。 3． 结账前完成所有进口件的发票匹配工作。 | 1．此部分数据需根据订单币种分为二部分导入(CNY和外币)。 2．外币订单的暂估视数据量可手工处理。 3． EE 中packing slip 字段存放 eb2中ship_date,比如: eb2: ship_date = “09/23/11”, receiver number = “RC12345” 可变为“C12345XX”,X代表收货单行的个数 4．该部分处理产生的PPV科目的余额将在GL中reversed 掉。
|  |  | 19 | 转换为excel文件，转换相关数据 | Davis |  |  | 1
|  |  | 20 | 生成 PO Receiver的cimload 文件 | Roger |  |  | 1
|  |  | 21 | 通过客户化的Purchase Order Receipts 程序cimload收货数据 | Roger |  |  | 4
|  |  | 22 | 完成cimload后，更新所有schedule order 的 fixed price = “no | Roger |  |  | 0.5
|  |  | 23 | 用户确认 | 张元琼
|  |  | 24 | backup
AP暂估 – 库存清零 | 2011-12-06 | 9:00-10:30 | 25 | 导出EE系统现有库存 | Roger |  |  | 0.5
|  |  | 26 | 转换cimload文件 | Roger |  |  | 0.5
|  |  | 27 | 通过计划外出库将现有库存清零 | Roger |  |  | 0.5
供应商日程订单累计接收量清零 |  |  | 28 | 供应商日程订单累计接收量重设 | Roger |  |  | 1
期末库存余额 | 2011-12-05 | 13:00-17:00 | 29 | 提取eb2系统中Inventory detail by location (3.6.16) 的库存余额数据 | 张科 |  |  | 1 | 1． 比较Eb2系统的Inventory detail by location (3.6.6)和EE 系统报表 3.2。 | 1.QADeb2系统中所有库存余额都需要转移到EE系统。所有库存余额包括正负数量，不含零记录。 2. Eb2中的所有库位在EE系统中都存在，即有唯一对应库位存在。准备动态数据前，再从EE系统导出一份location list提供给张科。 3. Work center 中费率保持和eb2 一致。 | 1.AP 暂估需及时完成。(AP 发票匹配完成) 2．12月份，所有库存相关事务都需及时在eb2系统完成。 3．年底有实际大盘点须及时在eb2系统中更新。 4．可在eb2系统中执行Zero BalanceDelete/Archive，减少无用数据量。 5．Eb2系统中若有负库存存在，请确认是否符合实际业务需要。目前情况来看，负库存可能只存在于巴南工厂逻辑库位。 6．各工厂(地点)明确库存余额的负责人，核对相关数据。 7．若存在新旧系统库存余额的成本差异，财务需做相应处理。 8．若客户寄售库存明细在eb2系统存在，需确保该类型库位所有的库存全部都是寄售性质的，若不是需转移到其他库位，不允许有负库存存在。 9.清理负库存，11月底前完成。 | 1． 先导入ITEM & LOCATION 状态代码，后导入item & location 状态明细。 2.含客户寄售库存余额在eb2系统内存在。准备细节请见“期末客户寄售库存余额”。 3.转换过程中涉及到的库存的对应科目使用渡科目。 4. 用户可参考报表96.6.15。
|  |  | 30 | 将上述提取数据转换为excel文件，转换site | 张科 | inventory balance.xls |  | 1
| 2011-12-06 | 10:30-11:30 | 31 | 根据excel文件准备EE系统unplanned receipt生成cimload格式的导入文件 | Roger |  |  | 0.5
|  |  | 32 | Cimload到EE系统 | Roger |  |  | 0.5
|  |  | 33 | 用户确认 | 张科
期末客户寄售库存余额 | 2011-12-05 | 13:00-17:00 | 34 | 根据要求准备excel文件，包括寄售库存数据 | 张科 | CS inventory balance.xls |  | 1 | 1．excel文件中的数据和EE系统报表7.18.4.1核对。 | 1． 此客户寄售库存指已发货给FORD,CHANGAN, SUZUKI三大客户，但是金税发票尚未开具的产品数量。即AR未开票应收数量。 | 张科负责所有协调，eb2客户日程订单的整理工作11月18号前完成。 1．年底前及时完成与有关客户的对账工作，准确的完成客户寄售库存数据的准备。 2．该数据除正常库存余额数据外，还需包括对应的客户日程订单，行号信息。 3．客户寄售库存明细在系统有体现，明确对应库位。保证该库位上所有库存都是属于客户寄售性质的。 4．寄售库位不能存在负库存，11月底前完成。 | 1．可能存在同一寄售物料对应多个客户日程订单，在准备excel时一定要分清各物料对应的客户日程订单和对应行号。 2．导入所涉及到科目统一使用过渡科目。
| 2011-12-06 | 11:30-12:30 | 35 | excel文件生成寄售库存余额初始化的cimload格式的导入文件 | Roger |  |  | 0.5
|  |  | 36 | 再导入寄售库存余额的初始化(7.18.25.1) | Roger |  |  | 1
|  |  | 37 | 用户确认 | 张科
期末未结采购订单 | 2011-12-05 | 9:00-17:00 | 38 | 提取eb2系统中的未结非生产性采购订单数据 | Roger | ??? |  | 1 | 比较Eb2系统的95.1.10 报告与EE 系统open PO report (5.9.1)， 用户在EE系统报表上签字确认。 | 导入EE系统订单的order quantity 是eb2中未收货数量 | 1.年底前控制从MAXIMO系统导入的订单数量 2． 已存在QAD系统的采购订单，尽量在年底前按时收货，并要求供应商及时提供发票，AP及时匹配，减少未结订单数量和AP暂估的数量。 3． 清理eb2中不需要的采购订单。 | 1． Cimload 需多次进行，文件区分PO header & line, CNY / others, taxable / no. 2.与MAXIMO开发人员明确需要直接更新的客户化字段。
|  |  | 39 | 将上述提取数据转换为excel文件，用户转换采购科目 | 昌琼 |  | 科目对照表 | 6
| 2011-12-06 | 13:00-17:00 | 40 | 根据excel文件准备EE系统PO所需cimload格式的导入文件 | Roger |  |  | 1
|  |  | 41 | Cimload到EE系统 | Roger |  |  | 2
|  |  | 42 | 提取eb2系统中的未结非生产性采购订单数据中MAXIMO相关的客户化字段，写程序直接更新到EE系统。 | Roger | ??? |  | 1
|  |  | 43 | 用户确认 | 蔡中华
供应商日程计划 | 2011-12-05 | 9:00-17:00 | 44 | 根据数据收集模板准备日程计划数据 | 方英 | SS release.xls |  | 4 | 1． 比较Eb2系统的5.5.3.13 报告与EE 系统，用户在EE系统报表上签字确认 | 2011年最后一周的有效日程计划 | 1．12/26日及时完成供应商日程计划。 | 1． Cimload 需多次进行，分header & line
| 2011-12-06 | 17:00-19:00 | 45 | 根据上述excel文件准备EE系统所需cimload格式的导入文件 | Roger |  |  | 1
|  |  | 46 | Cimload到EE系统 | Roger |  |  | 1
|  |  | 47 | 用户确认 | 方英
供应商日程订单累计接收量 | 2011-12-06 | 19:00-20:00 | 48 | 供应商日程订单累计接收量重设 | Roger | SS Cum Received.xls |  | 1
|  |  | 49 | 用户确认 | 方英
采购送货单 | 2011-12-07 | 9:00-11:00 | 50 | 根据数据收集模板准备采购收货单数据 | 方英 | openASN.xls |  | 4 | 5.5.5.5 eb2 vs. EE
|  |  | 51 | 根据上述excel文件准备EE系统所需cimload格式的导入文件 | Roger |  |  | 1
|  |  | 52 | Cimload到EE系统 | Roger |  |  | 1
|  |  | 53 | 用户确认 | 方英
准备工作 | 2011-12-07 | 11:00-12:00 | 54 | 导入item & inventory status | roger |  |  | 1
|  |  | 55 | backup
|  |  | 56 | 查看月底汇率设置
期末AR余额 | 2011-12-07 | 9:00-12:00 | 57 | 抽取AR余额明细数据 | Roger | ?? |  | 0.5 | 1． Eb2 96.5.1 报告vs EE 系统AR系统报告。按entity汇总，科目币种汇总。 | 1 使用历史价格. 2.外币科目使用当前汇率，即12/31的汇率。 | 1． 减少AR未结数量。 2．现在开始清理应收账款，如负数的调整等等。 | 1．余额需要按会计单位区分 2．所有余额需要根据科目类型进行区分，包括应收账款、其他应收款-押金类。 3．期末eb2要完成revaluation的程序后，才能开始提取数据。
|  |  | 58 | 转换为AR余额明细的EXCEL文件 | Davis |  |  | 1
|  |  | 59 | 在excel中完成entity的区分 | 陈玲 |  |  | 4
|  |  | 60 | 转换EE AR导入所需格式 | 陈玲 | CustomerOpeningBalance.xls |  | 1
| 2011-12-07 | 13:00-17:00 | 61 | 利用EE AR opening balance | Davis |  |  | 1
|  |  | 62 | 用户确认 | 陈玲
期末FA余额 | 2011-12-07 | 13:00-17:00 | 63 | 提取FA xxfaaorp.p (96.3.1) 明细数据转换为EXCEL文件 | 秦娅 | xxfaaorp.p (96.3.1) |  | 1 | 1． Eb2 96.3.1 报告vs EE FA 系统报告。按新旧科目分类汇总， entity汇总。 | 1． 使用eb2现有客户化程序xxfaaorp.p (96.3.1)提取现有FA 的明细记录，该明细账应与总账FA相关科目一致。 | 1． 尽早完成12月份FA的处理，12/19截止转固申请。12/20-12/21完成固定资产结账。可提前开始准备导入数据。 2． FA类型和库位，科目EE系统与eb2有所不同，确定区分原则。 | 1.导入eb2 FA Book “USA”. 2.Tag number 转换到 insurance company 字段。 3.确认字段变化内容，分类，库位，折旧费用子科目。 4.已报废固定资产(已清理，原值为零)不需带到EE系统.，已提完折旧资产需转入(资产仍存在)。
|  |  | 64 | 在excel中完成相应修改，如类型，地点，科目，设备号等 | 秦娅 |  |  | 4
| 2011-12-08 | 9:00-12:00 | 65 | 转换EE FA导入所需格式 | Roger |  |  | 1
|  |  | 66 | Cimload 系统 | Roger |  |  | 3
|  |  | 67 | 用户确认 | 秦娅
期末AP余额 | 2011-12-07 | 9:00-17:00 | 68 | 根据AP 余额明细数据 | Roger | ?? |  | 0.5 | 1． EB2 96.4.2 报告vs EE AP Aging 系统报告。按entity汇总，科目币种汇总。 | 1．使用eb2现有客户化程序xxapvorp.p (96.4.1/2)提取现有AP 的明细记录，该明细账应与总账AP科目一致。 2． 使用历史价格. 3． 外币科目使用当前汇率，即12/31的汇率。 | 1． 减少AP未结数量。 2． 现在开始清理应付账款，如负数的调整等等。 3． 员工报销清理。 | 1．AP余额不需要按会计单位区分，集中在会计单位2000公共管理下 2存在一个供应商有应付和其他应付款-押金；建立二个供应商代码 3．一个供应商预付款有多种类型存在，建立多个sub-acct代码。 4.所有余额需要根据科目类型进行拆分，比如说应付，其他应付，预付款，票据，员工借款等。 5.应付票据余额按供应商票据到期日汇总，导入EE系统，期初付款动作需要用户手工处理。 6．员工借款余额按借款明细导入EE系统，陈玲负责提供截止到12月底的员工借款明细(提取建立员工供应商数据)。 7期末eb2要完成revaluation的程序后，才能开始提取数据。
|  |  | 69 | 转换为AP余额明细的EXCEL文件 | Davis |  |  | 1
|  |  | 70 | 转换EE AP导入所需格式 | 张元琼 | SupplierOpeningBalance.xls |  | 6
|  |  | 71 | 根据AP模板，准备个人借款余额的明细 | 陈玲 | SupplierOpeningBalance.xls |  | 2
| 2011-12-08 | 13:00-17:00 | 72 | 利用EE AP opening balance导入期初余额 | Davis |  |  | 3
|  |  | 73 | 用户确认
期末GL余额 | 2011-12-08 | 9:00-17:00 | 74 | 提取GL TB 25.15.4 明细数据转换为EXCEL文件， 只取资产负债表科目 | 秦娅 | GL TB 25.15.4 |  | 1 | 1． Eb2 TB 25.15.4 报告vs excel 准备文件一致，按新旧科目分类汇总，entity汇总。 | 1．eb2中总账和子模块明细账应该一致。 2．相关外币科目使用12/31日汇率。 | 1．熟悉Entity拆分原则，方法 2．熟悉新旧科目对照关系，了解如何转换科目. 3．试做一个月的新旧科目转换，及会计单位的拆分。 4. 某些科目余额新旧系统有差异，如何处理，需及时在eb2系统总账处理。 | 1． 只取资产负债表的科目余额 2． 新旧科目对照,包括科目，子科目，成本中心，项目代码 3．部分系统科目要采用过渡科目。 4.期末eb2要完成revaluation的程序后，才能开始提取数据. 5． RV 凭证若存在，手工处理
|  |  | 75 | 在excel中完成新旧科目转换。 | 秦娅 |  | 科目对照表 | 2
|  |  | 76 | 在excel中完成entity的拆分 | 秦娅 |  |  | 4
|  |  | 77 | 将相关系统科目如control account转换为过渡科目 | 秦娅 |  |  | 1
|  |  | 78 | 转换成EE GL导入所需格式 | 秦娅 | journalentry.xls |  | 1
| 2011-12-09 | 9:00-17:00 | 79 | 利用JL excel integration 导入 | Davis |  |  | 2
|  |  | 80 | 准备相关调整凭证，如VAT税科目的导入 | 秦娅 |  |  | 1
|  |  | 81 | 输入相关调整凭证 | 秦娅 |  |  | 1
|  |  | 82 | 用户确认 | 秦娅
Note on I1: Author: 根据模拟测试情况 调整

## Account Combi
Account 组合
Account Type Sub-Acct Cost Center Project SAF
Bank Account Yes No No No
Cash Account Yes Yes Yes Yes
Closing Account Yes No No No
Cross-Company Account No No No No
Customer Control Account Yes Yes Yes No
Customer Payment Account Yes Yes Yes Yes
Fixed Assets Account Yes Yes Yes Yes
Inventory Control Account Yes Yes Yes Yes
Open Items Account Yes Yes Yes Yes
Standard Account Yes Yes Yes Yes
Supplier Control Account Yes Yes Yes No
Supplier Payment Account Yes Yes Yes Yes
Tax Account Yes No No No
WIP Control Yes Yes Yes Yes
System Accounts
Conversion (for conversion
activity only)
N/A N/A N/A N/A
PO Receipts Yes Yes Yes Yes
Realized Exchange Gain Yes No No No
Realized Exchange Loss Yes No No No
Result of Current Year Yes No No No
Result of Previous Year Yes No No No
Rounding Differences Yes No No No
Unmatched Invoices Yes No No No
Unrealized Exchange Gain Yes No No No
Unrealized Exchange Loss Yes No No No

## AccountSample
| 基础设置 |  | 菜单
| RW STD'CST = 20 |  | 1.4.1
| BOM Qty = 2 |  | 13.5
| Labor = 1 |  | 14.5/14.13.13
| Burden = 2 |  | 14.5/14.13.13
| FG STD'CST = 43 |  | 13.12.13
序号 | 事件 | D/C | 科目 | Type | 描述 | 金额 | 归属 | 类别 | 备注 | 菜单
1 | 股东投资,1000 CNY | D | 116001 | A | 银行存款 | 1000 | Bank Account | [1]
|  | C | 2999101 | L | 所有者权益 | 1000 | Standard Account | [2]
2 | 材料购买，收货 | D | 150001 | A | 原料库存 | 200 | Inventory | [3]
| 价格20(不含税),数量10. VAT 17% | C | 252001 | L | 材料采购 | 200 | System Control | [4.1] | PO Receipt
3 | 收到供应商发票,未匹配(SI) | D | 250001 | L | 未批准的凭证 | 200 | System Control | [4.2] | Unapprove Invoiced
| 20 * 10 = 200 + 34 = 234 | D | 140001 | A | 进项税 | 34 | VAT | [5]
|  | C | 200001 | A | 应付款 | 234 | Supplier Control Account | [6]
4 | 进行采购匹配,收货单(Matching) | D | 252001 | L | 材料采购 | 200 | System Control | [4.1]
|  | C | 250001 | L | 未批准的凭证 | 200 | System Control
|  | D/C | 6740101 | E | 价格/数量差异 | 0 | Standard Account
5 | 生产发料 | D | 155001 | A | WIP科目 | 200 | WIP Control Account | [7]
| 10(Qty) * 20(STD) = 200 | C | 150001 | A | 原料库存 | 200 | Inventory
6 | 成品入库
| 5(Qty) * 43(STD) = 215 | D | 150001 | A | 成品库存 | 215 | Inventroy
| 43 = 20(原料成本)*2(单位用量) + | C | 155001 | A | WIP 科目 | 215 | WIP Control Account
1(人工) + 2(直接成本)
7 | 工单结算 | D | 155001 | A | WIP科目 | 15 | WIP Control Account
|  | C | 5120101 | E | 人工吸收 | 5 | Standard Account
|  | C | 5220101 | E | 制造吸收 | 10 | Standard Account
8 | 销售出货 | C | 150001 | A | 成品库存 | 215 | Inventroy
| 5(Qty) | D | 5000101 | E | COGS 材料 | 200 | Standard Account
|  | D | 5100101 | E | COGS 人工 | 5 | Standard Account
|  | D | 5200101 | E | COGS 制造 | 10 | Standard Account
9 | 发票过帐 | D | 130001 | A | AR | 351 | Customer Control Account | [8]
| 5(Qty) * 60 = 300 | C | 4000101 | I | Sales Income | 300 | Standard Acccount
| 300 * 17% = 51 | C | 240001 | L | 销项税 | 51 | VAT
10 | 工资发放 | D |  | E | 工资 | 25 | Standard Account
|  | C | 116001 | A | 银行 | 25 | Bank Account
|  |  | 例子 |  |  |  | 销售收入 | 4000101 | 300 | Cr
| Customer Payment Account |  | 138001 | A | AR PIP | [9] | 销售成本COGS
| Supplier Payment Account |  | 208001 | L | AP PIP | [10] | 材料 | 5000101 | 200 | Dr
| Open Items Account |  | 248001 | L/A | Accruals | [11] | 人工 | 5100101 | 5 | Dr
| Closing Account |  | 350001 |  | 本年利润/往年 | [12] | 制造 | 5200101 | 15 | Dr
| Cross-Company Control |  | 195001 | A | AR往来科目 | [13] | 已吸收
| Cash |  |  |  | 现金 | [14] | 人工 | 5120101 | 5 | Cr
| Fixed Asset |  | 300001 | A | 固定资产 | [15] | 制造 | 5220101 | 15 | Cr
[7 empty] | 实发工资 |  | 25 | Dr
| System Account | [5 empty] | Profile/Loss | 290001 | 75 | Cr
| Conversion |  | 199001 | A |  | 1
| Unapproved invoices |  | 250001 | L |  | 2 | Balance Sheet
| PO Receipts |  | 252001 | L |  | 3 | 银行存款 | 116001 | 975 | Dr
| Expensed Item Receipts |  | 255001 | L |  | 4 | 库存 | 150001 | 0 | Dr
| Retained Earnings |  | 290001 | A |  | 5 | 应收款 | 130001 | 351 | Dr
| Result Previous Year |  | 292001 | L |  | 6
AR/AP | Unrealized exchange gain |  | 890001 | I |  | 7 | 应付款 | 200001 | 234 | Cr
PAY | Realized exchange gain |  | 895001 | I |  | 8 | 进项税 | 140001 | 34 | Dr
| Rounding Differences |  | 980001 | E |  | 9 | 销项税 | 240001 | 51 | Cr
AR/AP | Unrealized exchange loss |  | 990001 | E |  | 10 | 所有者权益 | 2999101 | 1000 | Cr
PAY | Realized exchange loss |  | 995001 | E |  | 11 | 当年利润 | 290001 | 75 | Cr

## OustandingList
序号 | 事件 | 类别 | 菜单 | 备注
1 | Report Cystal 如何安装 | 技术 | 28.9.9.7 28.17.9 | 加入文件至CRRuntime
2 | Product/Demo DB 时如何使用 XML目录 | 技术
3 | 只有AR/AP 使用额外科目进行重估记录. 银行科目重估放入XX科目 | 财务
4 | I/E 的期间发生额查询 | 财务
5 | GL 导入模板 | 财务
6 | Fixed Asset | 财务
7 | B/S & P/L 格式定义 | 财务
8 | Mask 的使用 Domain设定 | 财务
9 | ReRevalue 重估功能 - 包括N种 | 财务
10 | DayBook Type : Operational/FINANCIAL区别 | 财务 |  | AR=>Operational
11 | JE Save as Draft? Approve? | 财务
12 | 25.13.24 定义不可进行负数，是否有效? | 财务
13 | Credit Terms 多个到期日,如何显示？如何反映? | 财务
14 | SAF的默认机制 | 财务
15 | 成本计算方法 Period Cost ? FIFO / AVG | 财务
16 | Open Item Account/Cash Account 在那里使用 | 财务 |  | AP/AR 暂估调整科目
17 | 转仓 DR/CR 库存Account 如何使用？ | 财务
18 | COA Cash Type 使用 | 财务 | 31.2.1 | Petty Cash Create
19 | Conditon Staring As | 财务
20 | Invoice Upper Limit 使用在金税软件中,规定发票的最高发票金额! | 财务
21 | 转仓金额没有红冲 | 财务
22 | Account "Quantity" 为何在BC Balance view没有更新? | 财务

## DayBook
Record ID | Daybook Code | Daybook Description | Menu | SamSong'DB | Active | Daybook Type | Project Provision | Daybook Ctrl | Layer Code | Daybook Group Code | Daybook Groups Enabled | Access Role
tJournal.Journal_ID | tJournal.JournalCode | tJournal.JournalDescription | WhereToUse |  | tJournal.JournalIsActive | tJournal.JournalTypeCode | tJournal.JournalIsProjectProvision | tJournal.JournalControl | tJournal.tcLayerCode | tJournal.tcJournalGroupCode | tJournal.tlJournalGroupsIsEnabled | tJournal.tcRoleName
3626945 | BEUSD | Banking USD | 31.1.1 | 7BEUSD00 | TRUE | BANKINGENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3633696 | BECNY | Banking CNY | 31.1.1 | 7BECNY00 | TRUE | BANKINGENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3626946 | CASHIN | Cash Receipts |  | 7CASHIN0 | TRUE | CASHENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3626960 | CONEAOF | Consolidation EAST official |  | 7CONEAOF | TRUE | CONSOLIDATION | FALSE | FINANCIAL | Primary |  | FALSE
3626968 | SUPADJ | Supplier open item adjustments | 25.13.5 | 7SUPADJ0 | TRUE | CREDITORADJUSTMENT | FALSE | FINANCIAL | Primary |  | FALSE
3626966 | SCN | Supplier Credit Notes | 28.1.1.1 | 7SCN0000 | TRUE | CREDITORCREDITNOTE | FALSE | FINANCIAL | Primary |  | FALSE
3626951 | SCCOR | Correct Supplier CN | 28.1.1.1 | 7SCCOR00 | TRUE | CREDITORCREDITNOTECORRECT | FALSE | FINANCIAL | Primary |  | FALSE
3626967 | SINV | Supplier invoices | 28.1.1.1 | 7SINV000 | TRUE | CREDITORINVOICE | FALSE | FINANCIAL | Primary |  | FALSE
3630164 | SOB | Supplier Opening Balance | 28.1.15 | 7SOB0000 | TRUE | CREDITORINVOICE | FALSE | FINANCIAL | Primary |  | FALSE
3626950 | SICOR | Corredt supplier invoices | 28.1.1.1 | 7SICOR00 | TRUE | CREDITORINVOICECORRECT | FALSE | FINANCIAL | Primary |  | FALSE
3626969 | APPAY | Supplier Payments | 28.9.3.1 | 7APPAY00 | TRUE | CREDITORPAYMENT | FALSE | FINANCIAL | Primary |  | FALSE
3626965 | CUSTADJ | Open item adjustment customers | 25.13.5 | 7CUSTADJ | TRUE | DEBTORADJUSTMENT | FALSE | FINANCIAL | Primary |  | FALSE
3631787 | CA | Customer Adjustments |  | 7CA00001 | TRUE | DEBTORADJUSTMENT | FALSE | OPERATIONAL | Primary |  | FALSE
3626995 | CN | Customer Credit Note | 27.1.1.1 | 7CN00001 | TRUE | DEBTORCREDITNOTE | FALSE | OPERATIONAL | Primary |  | FALSE
3631784 | 217CCN | Customer Credit Notes | 27.1.1.1 | 7CN00000 | TRUE | DEBTORCREDITNOTE | FALSE | FINANCIAL | Primary |  | FALSE
3626949 | CCCOR | Correct customer CN | 27.1.1.1 | 7CCCOR00 | TRUE | DEBTORCREDITNOTECORRECT | FALSE | FINANCIAL | Primary |  | FALSE
3629498 | CCN | Customer Credit Note Corrections | 27.1.1.1 | 7CCN0001 | TRUE | DEBTORCREDITNOTECORRECT | FALSE | OPERATIONAL | Primary |  | FALSE
3626952 | FINCH | Finance Charge | 27.1.1.1 | 7FINCH00 | TRUE | DEBTORFINANCECHARGE | FALSE | FINANCIAL | Primary |  | FALSE
3626943 | CINV | Customer Invoices | 27.1.1.1 | 7CINV001 | TRUE | DEBTORINVOICE | FALSE | OPERATIONAL | Primary |  | FALSE
3630163 | COB | Customer Openning | 27.1.10 | 7COB0000 | TRUE | DEBTORINVOICE | FALSE | FINANCIAL | Primary |  | FALSE
3631785 | CICOR | Customer Invoice Corrections | 27.1.1.1 | 7CICOR01 | TRUE | DEBTORINVOICECORRECT | FALSE | OPERATIONAL | Primary |  | FALSE
3626970 | ARPAY | Default customer payments | 27.6.4.1 | 7ARPAY00 | TRUE | DEBTORPAYMENT | FALSE | FINANCIAL | Primary |  | FALSE
3626944 | JE | Default Journal Entry | 25.13.1.1 | 7JE00000 | TRUE | JOURNALENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3626973 | SYS-DB | SYSTEM DAYBOOK | 888888888 | 7SYS-DB1 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626994 | FA | FIXED ASSETS DAYBOOK |  | 7FA00001 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626993 | PL to RE | P& L to retained earnings |  | 7PLtoRE0 | TRUE | JOURNALENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3626989 | WORCT | WO Receipts | 16.11 | 7WORCT01 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626988 | WOISS | WO Issues | 16.10 | 7WOISS01 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626987 | WOCLOSE | WO Close | 16.21 | 7WOCLOSE | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626986 | WOMVAR | WO Material Usage variance | 16.21 | 7WOMVAR1 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626985 | JEIC | Intercompany daybook JE |  | 7JEIC001 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626984 | RCT-UNP | Unplanned receipt | 3.9 | 7RCT-UNP | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626983 | ISS-PRV | PO return to supplier | 3.8 | 7ISS-PRV | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626982 | ISS-UNP | Unplanned issue | 3.7 | 7ISS-UNP | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626981 | RCT-SOR | Inv. SO return | 3.11 | 7RCT-SOR | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626980 | RCT-PO | PO receipts | 5.13.1 | 7RCT-PO1 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626979 | ISS-SO | SO shipments | 7.9.15 | 7ISS-SO1 | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626978 | ICDEFDB | Inventory control Daybook |  | 7ICDEFDB | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626977 | USSYSDB | US system daybook |  | 7USSYSDB | TRUE | JOURNALENTRY | FALSE | OPERATIONAL | Primary |  | FALSE
3626976 | MEMO | Only in transient JE | 25.13.1.1 | 7MEMO000 | TRUE | JOURNALENTRY | FALSE | FINANCIAL | Trans-Memo |  | FALSE
3626975 | TRAJE | JE to approve | 25.13.1.8 | 7TRAJE00 | TRUE | JOURNALENTRY | FALSE | FINANCIAL | Trans-Approve |  | FALSE
3626974 | Template | Posting Templates JE | 25.13.1.1 | 7Templat | TRUE | JOURNALENTRY | FALSE | FINANCIAL | Trans-Template |  | FALSE
3626971 | SIREC | Default Matching entry | 28.1.1.1 | 7SIREC00 | TRUE | MATCHINGENTRYCIREC | FALSE | FINANCIAL | Primary |  | FALSE
3626963 | MFPCTRDB | Periodic Costing Transient Daybook |  | 7MFPCTRD | TRUE | PERIODICCOSTING | FALSE | OPERATIONAL | Trans-Approve |  | FALSE
3626964 | SUPPREVA | Revaluation Open Items Suppliers |  | 7SUPPREV | TRUE | REVALCREDITOR | FALSE | FINANCIAL | Primary |  | FALSE
3626959 | SPREVAL | Revaluation sup paym |  | 7SPREVAL | TRUE | REVALCREDITORDOC | FALSE | FINANCIAL | Primary |  | FALSE
3626953 | CUSTREVA | Revaluation open items customers |  | 7CUSTREV | TRUE | REVALDEBTOR | FALSE | FINANCIAL | Primary |  | FALSE
3626958 | CPREVAL | Revaluation cust paym |  | 7CPREVAL | TRUE | REVALDEBTORDOC | FALSE | FINANCIAL | Primary |  | FALSE
3626955 | GLREVAL | Revaluation GL |  | 7GLREVAL | TRUE | REVALGL | FALSE | FINANCIAL | Primary |  | FALSE
3626956 | ICREVAL | Revaluation intercompany |  | 7ICREVAL | TRUE | REVALINTERCO | FALSE | FINANCIAL | Primary |  | FALSE
3626957 | TAXREVAL | Revaluation tax |  | 7TAXREVA | TRUE | REVALVAT | FALSE | FINANCIAL | Primary |  | FALSE
3626947 | REVJE | Reversing Journal Entries |  | 7REVJE00 | TRUE | REVERSINGENTRY | FALSE | FINANCIAL | Primary |  | FALSE
3626962 | SELFBILL | Self-Billing Daybook |  | 7SELFBIL | TRUE | SELFBILLINVOICE | FALSE | FINANCIAL | Primary |  | FALSE
3626961 | PL Close | P&L Closing |  | 7PLClos0 | TRUE | YEARCLOSING | FALSE | FINANCIAL | Primary |  | FALSE
Note on B2: The maximum length for this field is 8 characters.
Note on C2: The maximum length for this field is 40 characters.
Note on F2: TRUE = True FALSE = False
Note on G2: BANKINGENTRY = Banking Entries CASHENTRY = Cash Entries CONSOLIDATION = Consolidation CREDITORADJUSTMENT = Supplier Adjustments CREDITORCREDITNOTE = Supplier Credit Notes CREDITORCREDITNOTECORRECT = Supplier Credit Note Corrections CREDITORINVOICE = Supplier Invoices CREDITORINVOICECORRECT = Supplier Invoice Corrections CREDITORPAYMENT = Supplier Payments DEBTORADJUSTMENT = Customer Adjustments DEBTORCREDITNOTE = Customer Credit Notes DEBTORCREDITNOTECORRECT = Customer Credit Note Corrections DEBTORFINANCECHARGE = Finance Charge DEBTORINVOICE = Customer Invoices DEBTORINVOICECORRECT = Customer Invoice Corrections DEBTORPAYMENT = Customer Payments JOURNALENTRY = Journal Entries MATCHINGENTRYCIREC = Matching Daybook PERIODICCOSTING = Periodic Costing REVALCREDITOR = Revaluation Suppliers REVALCREDITORDOC = Revaluation Supplier Payments REVALDEBTOR = Revaluation Customers REVALDEBTORDOC = Revaluation Customer Payments REVALGL = Revaluation GL REVALINTERCO = Revaluation Intercompany REVALVAT = Revaluation Tax REVERSINGENTRY = Reversing Entries SELFBILLINVOICE = Self-Bill Invoices YEARCLOSING = Year-End Closing
Note on H2: TRUE = True FALSE = False
Note on I2: EXTERNAL = External FINANCIAL = Financial OPERATIONAL = Operational
Note on J2: The maximum length for this field is 20 characters.
Note on K2: The maximum length for this field is 20 characters.
Note on L2: TRUE = True FALSE = False
Note on M2: The maximum length for this field is 20 characters.